## M&E
ANNEX 2
Monitoring and Evaluation Framework
Indicator ID# | Indicator | Baseline |  | Timeframe and targets
|  | Value | Year/ Source | 2017 | 2018 | 2019 | 2020 | 2021 | Source of Data
Goal: To Ensure a smooth transition from TGF funding towards fully national funding of HIV and TB national response by Year 2022
External Environment
Objective # 1: To create conducive legal environment to ensure smooth implementation of HIV and TB national response and achieve greater engagement of civil society organizations through public funding.
Political Environment
Objective 1.1.1. Create conducive legal environment for HIV national response
Activity 1.1.1.1. Increase Coordination among key players, relevant government bodies, Parliamentary committees, civil society, the National Platform on Drug Policy Reform
PE1 | Number of coordination meetings involving relevant stakeholders including the National Platform on Drug Policy Reform | NA | NA | 4 |  |  |  |  | Meeting minutes; meeting agendas; presentations; attendance list; media coverage
Activity 1.1.1.2. Monitor and foster policy interventions to remove the legislative barriers for access to HIV Prevention and harm reduction service in civil and penitentiary sectors
PE2 | Georgian Criminal Code and Administrative Offences Code revised and amendments adopted to remove barriers to HIV& harm reduction services | NA | NA | Yes |  |  |  |  | Adopted amendments posted on www.macne.gov.ge
PE3 | Georgia Framework Law on Drugs, Psychotropic Substances, Precursors and Narcological Aids revised and amendments adopted | NA | NA | Yes |  |  |  |  | Adopted amendments posted on www.macne.gov.ge
Activity 1.1.1.3. Support development and enforcement of the Four-pillar Drug Policy, Anti-Drug Strategy and Action Plan
PE4 | The 4-pillar Drug Policy, Anti-drug strategy and 3-year Action Plan developed | NA | NA |  | Yes |  |  |  | Drug Policy; Anti-drug Strategy; Action Plan
PE5 | The 4-pillar Drug Policy, Anti-drug strategy and costed Action Plan approved by Government resolution | NA | NA |  | Yes |  |  |  | Meeting minutes; Government resolution
Objective 1.1.2. Create enabling environment for CSO engagement in HIV & TB national response
Activity 1.1.2.1. Review State Procurement Law and relevant regulations to identify potential barriers for social contracting to deliver HIV services under the state funding
PE6 | State Procurement Law and relevant regulations reviewed and potential barriers for social contracting identified | NA | NA | Yes |  |  |  |  | Report outlining potential legal barriers for social contracting
Activity 1.1.2.2. Assess the barriers and opportunities for CSOs/CBOs to satisfy the state procurement requirements and in case of need – to develop and adopt detailed operational manual describing the rule and procedures for contracting CSOs /CBOs for health service delivery
PE7 | Barriers and opportunities for CSOs/CBOs to satisfy the state procurement requirements identified | NA | NA | Yes |  |  |  |  | Report outlining barriers and capacity of CSOs for participating in state tenders
PE8 | Detailed operational manual to support CSOs participation in state tendering developed | NA | NA | Yes |  |  |  |  | Operational manual
Activity 1.1.2.3. Build Capacity for CSOs/CBOs, their networks and coalitions – through training and technical assistance in management, resource mobilization for CSOs/CBOs to satisfy the state procurement requirements
PE9 | Number of training sessions and number of CSO/CBOs participated in training in management and resource mobilization to satisfy state procurement requirements (disaggregated by disease-focus) | NA | NA |  | 2 Training (Tbilisi); & 2 training (region); 10 CSOs/CBOs (HIV ) 10 CSOs/CBOs (TB) | 1 Training (Tbilisi), & 2 training (region); 10 CSOs/CBOs (HIV ) 5 CSOs/CBOs(TB) |  |  | Training attendance lists; training agenda; certificates
Internal Environment
Objective 2. To enhance structural, institutional and HR capacity of the country to implement and manage HIV/AIDS and TB interventions without interruption or compromising the scale, the scope and the quality of national HIV and TB national responses.
2.1.1. Financial resources
2.1.1.1. Financial Resources: HIV
Objective 2.1.1. Ensure full budgetary commitment and allocative efficiency for national HIV response
Activity 2.1.1.1. Conduct HIV program allocative and technical efficiency study to inform HIV strategic planning during the transition period
FIN1 | HIV Program efficiency study is conducted and the report is developed that is validated and approved by CCM | NA | NA | Yes |  |  |  |  | Study report; Validation meeting minutes; CCM meeting minutes on approval
FIN2 | Program Efficiency study findings inform HIV strategic planning during the transition period, including new NSP development process | NA | NA |  | Yes |  |  |  | Section in the new NSP describing to what extent study recommendations were considered
Activity 2.1.1.2. Support the Government of Georgia to establish a System of Health Accounts (SHA) that will regularly monitor HIV & TB expenditure data and generate reports that are publicly accessible
FIN3 | TA to support the GoG to establish a national SHA is provided | NA | NA | Yes | Yes |  |  |  | TOR; Mission report
Activity 2.1.1.3. Provide capacity building and TA to relevant local staff to ensure that the SHA is functioning properly
FIN4 | Relevant local staff is trained on SHA | NA | NA | At least 3 staff members trained | At least 6 staff members trained |  |  |  | Training attendance lists; training agenda; certificates
Activity 2.1.1.4. Conduct HIV/AIDS Spending data analysis on an annual basis
FIN5 | Comprehensive national AIDS spending analysis completed annually (GARP funding matrix) | NA | NA | Yes | Yes |  |  |  | Annual report on HIV spending; GARP funding matrix uploaded on public website
FIN6 | HIV spending data analyzed through the national SHA annually | NA | NA |  |  | Yes | Yes | Yes | Annual report on HIV spending; GARP funding matrix uploaded on public website
FIN7 | The share of public spending out of the total spending for HIV response (%) | 54.87% | 2015 / GARP | 57% | 62% | 67% | 72% | 77% | National HIV/AIDS spending data assessment
FIN8 | Total public spending on national HIV response (US $) | 8753885 | 2015 / GARP | 10,5 mln $ (NSP) | 12,45 mln $ (NSP) | TBD | TBD | TBD | National HIV/AIDS spending data assessment
Activity 2.1.1.5. Allocate commensurate funding for prevention programs targeting KAPs including low threshold services
FIN9 | Total public funding for HIV prevention services targeting MSM | 0 (out of $236,530) | 2015 GARP | 0 | 5783 | TBD | TBD | TBD | Program Budgets; AIDS spending data ; NASA reports; GARP Funding Matrix
FIN10 | Share of public spending out of the total spending for HIV prevention services targeting MSM (%) | 0% | 2015 GARP | 0% | 1% | TBD | TBD | TBD | Program Budgets; AIDS spending data ; NASA reports; GARP Funding Matrix
FIN11 | Total public funding for HIV prevention services targeting FSWs | 0 (out of $295,075 | 2015 GARP | 0 | 8169 | TBD | TBD | TBD | Program Budgets; AIDS spending data ; NASA reports; GARP Funding Matrix
FIN12 | Share of public spending out of the total spending for HIV prevention services targeting FSWs (%) | 0% | 2015 GARP | 0% | 3% | TBD | TBD | TBD | Program Budgets; AIDS spending data ; NASA reports; GARP Funding Matrix
FIN13 | Total public funding for HIV prevention services (excluding OST) targeting PWIDs | 0 (out of $1,518,895) | 2015 GARP | 0 | 56585 | TBD | TBD | TBD | Program Budgets; AIDS spending data ; NASA reports; GARP Funding Matrix
FIN14 | Share of public spending out of the total spending for HIV prevention services (excluding OST) targeting PWIDs (%) | 0% | 2015 GARP | 0% | 3% | TBD | TBD | TBD | Program Budgets; AIDS spending data ; NASA reports; GARP Funding Matrix
FIN15 | Total public funding for HIV prevention services, including OST targeting epidemiologically priority groups (MSM; FSWs, PWIDs) | 1989514 | 2015 GARP | $3,230,709 (NSP) | $3,833,860 (NSP) | TBD | TBD | TBD | Program Budgets; AIDS spending data ; NASA reports; GARP Funding Matrix
FIN16 | Share of public spending out of the total spending for HIV prevention services, including OST targeting epidemiologically priority groups (MSM; FSWs, PWIDs) | 35% | 2015 GARP | 39% (NSP) | 40% (NSP) | TBD | TBD | TBD | Program Budgets; AIDS spending data ; NASA reports; GARP Funding Matrix
Activity 2.1.1.6. Align state funds allocation to epidemiological priorities for each key population affected to ensure allocative efficiency
FIN17 | Data on AIDS spending by each KAP analyzed to assess allocative efficiency and report developed | NA | NA | Yes | Yes | Yes | Yes | Yes | AIDS spending annual report, which includes the section on allocative efficiency
Activity 2.1.1.7. Allocate state funding to support HIV related researches, including second generation studies (Population Size Estimation studies, IBBSs among KAPs)
FIN18 | Share of public spending out of the total spending on IBBSs & PSE among KAPs (%) annually | 0% | 2015 / GARP | 0 | 48% | 60% | 80% | >90% | Program Budgets; AIDS spending data ; NASA reports; GARP Funding Matrix; SHA report
Activity 2.1.1.8. Engage with relevant ministries (MoES, MoC, MoYS) and local governments, city mayors and municipalities to encourage their engagement in multi-sectoral HIV response
FIN19 | Number of coordination meetings and advocacy meetings conducted to encourage multi-sectoral HIV response disaggregated by the type of stakeholders/institutions (ministries, local governments, city mayors, municipalities) | NA | NA | 4 coordination meetings; | 4 coordination meetings; | 4 coordination meetings; | 4 coordination meetings; | 4 coordination meetings; | Meeting minutes; list of participants; meeting agendas; media coverage; photo gallery
FIN20 | Total resources (US$) mobilized outside the MoH | NA | NA |  | 100000 | 200000 | 300000 | 400000 | Specific reports; budgets of corresponding partner institutions/agencies; MoU or other formal agreement documents signed
2.1.2. Financial Resources: TB
Objective 2.1.2. Ensure adequate funding and allocative efficiency for the national TB response
Activity 2.1.2.1: Gradually fill the gaps in the financing of the National TB Program
FIN21 | The share of public spending out of the total spending for TB national response (%) | 46% | 2015 | 60% | 65% | 70% | 75% | 80% | National TB spending data assessment
FIN22 | Total public spending (US$) on national TB response | 12412132 | 2015 | TBD | TBD | TBD | TBD | TBD | National TB spending data assessment report
Activity 2.1.2.2: Ensure mobilization of funding for continuous education for TB personnel (funding sources for CPD courses)
FIN23 | Total spending for CPD courses for TB personnel | NA | NA |  |  |  | 136800 | 128400 | Spending data; participants' registration; Certificates
Activity 2.1.2.3. Conduct TB Spending data analysis on an annual basis
FIN24 | TB spending data analyzed through the national SHA annually | NA | NA |  |  | Yes | Yes | Yes | Annual report on TB spending uploaded on publicly accessible website
2.2. Resource Generation: Human resources and Infrastructure
2.2.1. Human Resources: HIV
Objective 2.2.1: Ensure adequate staffing in HIV response
Activity 2.2.1.1. Develop policy for production and continuous professional development of human resources for HIV/AIDS programs, including CSO personnel
HR1 | Policy for production and continuous professional development of HR for HIV response, including CSO personnel, developed | NA | NA |  | Yes |  |  |  | HR-CPD policy
HR2 | HR & CPD Policy approved by Government resolution | NA | NA |  |  | Yes |  |  | Government resolution
Activity 2.2.1.2. Integrate HIV training modules in the undergraduate and postgraduate education system
HR3 | Number of training modules on HIV/AIDS integrated into formal education system (undergraduate; postgraduate; and continuous education) | NA | NA |  | 10 modules | At least 5 | At least 5 | At least 5 | University curricula; syllabi; class schedules
Activity 2.2.1.3. Provide training of trainers, including that for academia staff on HIV related topics
HR4 | Number of TOTs conducted on HIV related topics | NA | NA |  | 3 ToTs in Tbilisi; 4 ToTs in regions | 3 ToTs in Tbilisi; 4 ToTs in regions | 4 ToTs in Tbilisi; 4 ToTs in regions | 4 ToTs in regions | ToT agenda; training materials, attendance list; certificates
HR5 | Number of academia staff/trainers trained to deliver HIV-related training courses within the formal educational system | NA | NA |  | At least 25 | At least 25 | At least 30 | At least 15 | ToT agenda; training materials, attendance list; certificates
2.2.2. Human Resource: TB
Objective 2.2.2.1 Scale-up and the nationwide implementation of the human resources plan and RBF mechanism for the integrated and patient-centered model of TB care
Activity 2.2.2.1.1: Monitoring of development and implementation of long-term master plan for the integrated model for TB services (focusing on HR)
HR6 | Monitoring of development and implementation of long-term master plan (focusing on HR) for the integrated model for TB services conducted and reports developed | NA | NA | Yes | Yes | Yes | Yes | Yes | Annual monitoring reports
Activity 2.2.2.1.2: Support the scale up of Results Based Financing (RBF) mechanism for nationwide implementation
HR7 | Number of institutions introducing RBF mechanism | NA | NA |  | TBD | TBD | TBD | TBD | Hospital data; interviews with stakeholders
Objective 2.2.2.2 Ensure production and continuous professional development of human resources for TB program, including policies for developing CSO personnel
Activity 2.2.2.2.1: Develop policy for production (professional competencies/qualification framework, course accreditation, and certification) for non-medical staff/CSO personnel as well as medical personnel of PHC
HR8 | Policy for production and continuous professional development of HR for TB programs, including CSO personnel developed | NA | NA |  | Yes |  |  |  | HR-CPD policy
Activity 2.2.2.2.2: Ensure allocation of public funding for Continuous Professional Development courses(see Indicator #FIN23)
Activity 2.2.2.2.3: Introduce free of charge residency courses for understaffed specialties, i.e. such as Pulmonology and Pthisiatry specialties
HR9 | Number of residents enrolled in free of charge residency course in TB | NA | NA |  | 3 enrolled in 3 year residency course | 3 enrolled in 3 year residency course | 3 enrolled in 3 year residency course | 3 enrolled in 3 year residency course | Ministerial decree or other formal resolution. Participants enrollment/admission notice
Activity 2.2.2.2.4: Ensure periodic updates for TB care guidelines
HR10 | TB care guidelines revised/developed and approved to be aligned with the WHO guidelines | NA | NA | As needed | As needed | As needed | As needed | As needed | Revised /developed guidelines; ministerial orders about the approval of guidelines
Activity 2.2.2.2.5: Support the institutionalization of TB training through integrating training modules into formal education system
HR11 | Number of TB-related training modules integrated into the formal education system (disaggregation by universities and by professions) | NA | NA |  | 5 modules | 5 modules |  |  | University curricula; syllabi; class schedule
Activity 2.2.2.2.6: Support the development of a network of training of trainers for TB
HR12 | Number of ToTs conducted | NA | NA |  | 3 Tots in Tbilisi; 3 ToTs in regions | 3 Tots in Tbilisi; 3 ToTs in regions |  |  | Training of Trainers materials; agenda; participants list; certificates
2.2.3. Infrastructure - Health and Non-Health equipment for HIV and TB
Activity 2.2.3.1. Provide preper O&M for Health and Non-health equipment for HIV and TB programis
IN1 | Frequency of failures of the major equipment used in HIV and TB programs | NA | NA | <10 | <10 | <10 | <10 | <10 | Monitoring reports
2.3 Health Information
2.3.1. Health Information: HIV
Objective 2.3.1. Sustainable development of Health Information System in HIV national response
Activity 2.3.1.1. Monitor and evaluate (by the end of 2017) the HIS strengthening interventions and the process of full integration of advance surveillance, monitoring and reporting system.
HIS1 | Monitoring and evaluation of HIS strengthening interventions under the GF project conducted and reports developed | NA | NA | Yes |  |  |  |  | Monitoring reports
Activity 2.3.1.2. Plan and implement measures identified through the planned HIS evaluation to support the full institutionalization of the HIS for HIV national response (TBD)
HIS2 | Action Plan for supporting the full institutionalization of the HIS for HIV national response developed | NA | NA |  |  | Yes | Yes |  | Detailed action plan for HIV HIS strengthening
HIS3 | Monitoring of the implementation of HIS strengthening intervention (after 2017) | NA | NA |  |  | Yes | Yes |  | Monitoring reports
2.3.2. Health Information System - TB
Objective 2.3.2: Improve the health information systems for TB
Activity 2.3.2.1: Monitor and evaluate (by the end of 2017) the process of full integration of advance monitoring and reporting system (planned under new TB grant)
HIS4 | Monitoring and evaluation of HIS strengthening interventions for TB under new GF TB grant conducted and reports developed | NA | NA | Yes |  |  |  |  | Monitoring reports
Activity 2.3.2.2: Plan and implement measures identified through the planned HIS evaluation to support the full institutionalization of the HIS for TB national response (TBD)
HIS5 | Action Plan for supporting the full institutionalization of the HIS for TB national response developed | NA | NA |  | Yes |  |  |  | Detailed action plan for TB HIS strengthening
HIS6 | Monitoring of the implementation of TB HIS strengthening intervention (after 2017) | NA | NA |  | Yes |  |  |  | Monitoring reports
Activity 2.3.2.3: Train TB staff in the information system's use.
HIS7 | Number of trainings (or TB staff trained) in the use of TB E-module information system | NA | NA |  | 3 training (Tbilisi) 5 training (regions); 160 staff | 2 training (Tbilisi) 5 training (regions); 140 staff |  |  | Attendance list; training agenda; certificates
2.4.1. Governance - HIV Governance (Political support, Program Leadership, Coordination)
Objective 2.4.1. Improve HIV program governance
Activity 2.4.1.1. Develop costed HIV/AIDS National Strategy for 2019-2023 and Action Plan
GOV1 | Costed HIV/AIDS National Strategy for 2019-2023 and Action Plan developed | NA | NA |  | Yes |  |  |  | Costed HIV/AIDS National Strategy for 2019-2023 and Action Plan
Activity 2.4.1.2. Advocacy for approval of the HIV/AIDS National Strategy for 2019-2023 and Action Plan by Government resolution
GOV2 | Costed HIV/AIDS National Strategy for 2019-2023 and Action Plan approved by Government resolution | NA | NA |  | Yes |  |  |  | Government resolution
Activity 2.4.1.3. Implement recommendations from the CCM evaluation study
GOV3 | Policy dialogues with officials and stakeholders carried out to implement recommendations from the CCM evolution study | NA | NA | TBD |  |  |  |  | Meeting minutes; participants list, ministerial order or other relevant Government resolution adopted regarding the CCM
2.4.2. Governance -TB
Objective 2.4.2 Improve governance for TB program
Activity 2.4.2.1: Ensure the codification of the roles and responsibilities for TB program implementation through the adoption of legal document (Government of Georgia resolution and possible changes to the TB Law)
GOV4 | TB program governance system defined and legally approved by Government resolution | NA | NA |  | Yes |  |  |  | Government resolution/ or adopted amendment to the TB State Law
Activity 2.4.2.2: Engage the relevant government agencies to explore and implement the regulatory mechanism for private providers to retain the TB services beyond the mandated period (2018).
GOV5 | Policy dialogue launched among relevant government agencies and private providers and suitable regulatory mechanisms for retaining private service providers in the TB services elaborated | NA | NA | Yes |  |  |  |  | Meeting minutes; orders; resolution; formal agreement; memorandum of understanding, etc.
GOV6 | Regulatory mechanism for retaining private service providers in the TB services is adopted and enforced | NA | NA |  | Yes |  |  |  | Written regulatory mechanism; ministerial order on enforcement
GOV7 | Percentage of private service providers retained out of all providers previously (as of 2018) engaged in TB service delivery | 40-45 private clinics | 2016/ NCDC data |  |  | 95% | 95% | 95% | Program data; agreement with service provider organizations; registry of TB service provider PHC
Activity 2.4.2.3. Develop costed TB National Strategy for 2021-2025 and Action Plan
GOV8 | Costed TB National Strategy for 2021-2025 and Action Plan developed | NA | NA |  |  |  | Yes |  | Costed TB National Strategy for 2021-2025 and Action Plan
Activity 2.4.2.4. Approve the TB National Strategy for 2021-2025 and Action Plan by the Government resolution to support its implementation
GOV9 | Costed TB National Strategy for 2021-2025 and Action Plan approved by Government resolution | NA | NA |  |  |  | Yes |  | Government resolution
2.5. Accountability
2.5.1. Accountability - HIV
Objective 2.5.1. Improve HIV program accountability to disseminate programmatic and financial data to key actors and wider public.
Activity 2.5.1.1. Develop program outcome dissemination and communication strategy to ensure transparency and access to programmatic and financial data.
ACC1 | Program outcome dissemination and communication strategy developed | NA | NA | Yes |  |  |  |  | Program outcome dissemination and communication strategy
Activity 2.5.1.2. Regularly publish and make accessible the programmatic and financial reports on HIV/AIDS program implementation to all interested parties, including the CBOs, beneficiaries and wider public.
ACC2 | HIV programmatic and financial reports published (per the approved Dissemination and Communication Strategy) and are accessible | NA | NA | Yes | Yes | Yes | Yes | Yes | HIV Programmatic and financial reports; NCDC & CCM websites. Dissemination meeting agendas; attendance list.
Objective 2.5.2 Improving accountability to ensure that the information (programmatic and financial) is transparent and publicly accessible
Activity 2.5.2.1: Regularly publish and make accessible the programmatic and financial reports on TB program implementation to all interested parties, including the CBOs and wider public.
ACC3 | TB programmatic and financial reports produced and are accessible | NA | NA | Yes | Yes | Yes | Yes | Yes | TB Programmatic and financial reports; NCDC & CCM websites. Dissemination meeting agendas; attendance list.
2.6. Service Delivery
2.6.1. Service Delivery - HIV
Objective 2.6.1. Improve HIV service delivery
Activity 2.6.1.1. Advocate for approval of HIV prevention and harm reduction service national standards.
SD1 | HIV prevention service national standards for each KAP (MSM&MSMW; FSWs) approved | NA | NA | Yes |  |  |  |  | Approval notification /formal resolution
SD2 | Harm Reduction service national standards approved | NA | NA | Yes |  |  |  |  | Approval notification /formal resolution
Activity 2.6.1.2. Train CSO staff to support implementation of national HIV prevention standards
SD3 | Number of HIV CSO staff trained in national HIV prevention /harm reduction service national standards | NA | NA |  | 25 | 25 |  |  | Training attendance list; training agendas
2.6.2. Service Delivery - TB
Objective 2.6.2 Support the implementation of the Integrated, patient-centered care and prevention model
Activity 2.6.2.1: Monitoring of development and implementation of long-term master plan for the integrated model for TB services (focusing on service models);
SD4 | Monitoring of development and implementation of long-term master plan for the integrated model for TB services conducted and reports developed | NA | NA | Yes |  |  |  |  | Annual monitoring reports
Activity 2.6.2.2: Support the implementation of the quality improvement systems (implementation of evidence based clinical practice guidelines, supportive supervision and performance review, quality measurement)
SD5 | Number of Training for TB providers in quality assurance (managers, PHC physicians, nurses | NA | NA | 4 training (Tbilisi) + 12 Training (regions) | 4 training (Tbilisi) + 10 Training (regions) | 4 training (Tbilisi) + 10 Training (regions) |  |  | Training materials; presentations, attendance lists; certificates
SD6 | Percentage of TB service providers that follow evidence-based clinical practice guidelines assessed through clinical audits | NA | NA |  | 50% | 70% | 90% | 90% | Hospital records; clinical (including internal) audit report
2.7. Procurement and Supply Chain Management
2.7.1. Procurement and supply chain management - HIV
Objective 2.7.1. Maintain the effective and functional procurement and supply chain for the HIV/AIDS health products by the relevant national structures
Activity 2.7.1.1: Perform the procurement and supply chain assessment (by the end of 2017) for HIV/AIDS health products
PSM1 | Assessment of procurement and supply chain management system for HIV performed and the assessment report developed | NA | NA | Yes |  |  |  |  | HIV Procurement and supply chain management system assessment report
Activity 2.7.1.2. Plan and implement capacity building for the national agency responsible for the procurement and supply chain management
PSM2 | Capacity building plan for the national agency responsible for the procurement and supply chain management developed | NA | NA |  | Yes |  |  |  | Capacity building plan
PSM3 | Number of trainings & number of staff members from the national agency responsible for the procurement and supply chain management trained | NA | NA |  | 2 trainings; at least 6 staff members |  |  |  | Training attendance lists; training agenda; certificates
2.7.2. Procurement and supply chain management - TB
Objective 2.7.2. Maintain the effective and functional procurement and supply chain for the TB health products by the relevant national structures
Activity 2.7.2.1: Perform the procurement and supply chain assessment (by the end of 2017) for TB health products
PSM4 | Assessment of procurement and supply chain management system for TB performed and repot developed | NA | NA | Yes |  |  |  |  | TB Procurement and supply chain management system assessment report
Activity 2.7.2.2. Plan and implement capacity building for the national agency responsible for the procurement and supply (if a new entity will take over the procurement responsibility)
PSM5 | Number of trainings & number of staff members from the national agency responsible for the procurement and supply chain management trained | NA | NA |  |  | 2 trainings; at least 6 staff members |  |  | Training attendance lists; training agenda; certificates
2.8. Organizational capacity
2.8.2. Organizational capacity - TB
Objective 2.8.2: Strengthen the organizational capacity of the dedicated TB management agency (TBD under governance component) to improve coordination and management of national programme
Activity 2.8.2.1: To implement capacity building activities in order to enhance the role of National TB Council (NTC) secretariat/the MoH Department of Health to provide operational and secretarial support to NTC as the coordination body for the national TB program
ORG1 | Number of the NTC secretariat/ the MoH Department of Health staff participating in training/study tours | NA | NA | 3 secretariat staff trained | 3 secretariat staff trained | Secretariat trained | Secretariat trained | Secretariat trained | Training materials; attendance list; training agenda; certificates
2.9. Transition Planning
2.9.1. Transition Planning - HIV and TB
Objective 2.9.1 Ensure that the TP is actionable and legally binding
Activity 2.9.1.1: Approve the TP with actionable indicators and milestones through the Government Resolution
TP1 | Transition Plan with actionable indicators and milestones approved through the Government resolution | NA | NA | Yes |  |  |  |  | Government resolution
Activity 2.9.1.2: Establish external Peer Review Mechanism for monitoring the implementation of Transition Sustainability Plan as well as TGF grants and National Strategic Plans for HIV and TB to promote adherence to and fulfilment of declared commitments from the State as well as other programs
TP2 | Designated M&E Unit established (TBD) | NA | NA |  | Yes |  |  |  | Formal documents about the Unit; TOR of staff members; contracts
TP3 | Operational Manual for Transition Plan Monitoring and Evaluation developed | NA | NA | Yes |  |  |  |  | Operational Manual for Transition Plan Monitoring and Evaluation
TP4 | M&E reports about achievements against the Transition Plan indicators produced annually and are accessible to public | NA | NA |  | Yes | Yes | Yes | Yes | Annual M&E reports uploaded on the NCDC, MOH, CCM websites